Project Proposal

SASTRA–TCS Technology Innovation Centre (TIC) — Call for Proposal

RIA-PoC: A Reconfigurable Tile-Based Edge-AI Accelerator on FPGA

| Domain | Artificial Intelligence (edge-AI hardware) |
| --- | --- |
| Duration | 18 months |
| Funding requested | Rs. 50.00 Lakh (capital + revenue) |
| Current TRL | TRL 2–3 (concept formulated; architecture defined on paper) |
| Target TRL | TRL 4–5 (technology validated in laboratory on representative workloads) |
| Institution | <Name of the Institution> |
| Principal Investigator | <PI name, designation, department> |
| Team | 1 PI, 1 Co-PI (VLSI / embedded systems), 2 project associates, 4 UG/PG students |

1. Executive Summary

Edge devices increasingly need to run machine-learning models locally, but the hardware options available to Indian product companies are unsatisfactory: fixed-function AI accelerators become obsolete when model architectures change, general-purpose processors are too power-hungry, and raw FPGAs demand hardware expertise that most product teams do not have.

This project will build and measure a proof-of-concept of the Reconfigurable Intelligence Architecture (RIA): a small array of four identical programmable compute tiles on an FPGA, where each tile can act as a matrix-multiply engine, a convolution engine, or a vector/activation engine depending on the instructions loaded into it. The same hardware, without re-synthesis, will be demonstrated on two representative edge workloads: a compact vision CNN and a 1-D ECG classification model. Success is defined by measured numbers — tile utilisation, energy per inference against the on-board embedded CPU, and model-swap time — not by claims.

2. Problem Statement and Motivation

Fixed accelerators age badly. NPUs hard-wired for one family of models (e.g., CNNs) waste silicon or fail outright when the deployed model changes; edge products live 5–10 years while model architectures turn over in 1–2.

The edge power budget rules out GPUs. Battery-powered and fanless devices operate in the milliwatt-to-watt range.

FPGAs are flexible but inaccessible. Every model change requires hours of synthesis and place-and-route plus digital design expertise — impractical for AI/product teams.

The gap this project addresses: an accelerator whose function can be changed in software, in seconds, while remaining far more energy-efficient than an embedded CPU. The insight that makes this tractable is that the bulk of the computation in practically every ML model is multiply-accumulate work plus a thin layer of vector operations (activations, normalisation, pooling); what differs between models is the order and proportion in which these primitives are used — and that can be expressed as instructions rather than as circuit structure.

3. Objectives

The project deliberately proposes a narrow, measurable scope:

O1. Design and verify the RTL of one programmable compute tile: a MAC (multiply-accumulate) array, a small vector unit with activation support, local buffer memory, and an instruction sequencer, operating on INT8/INT16 data.

O2. Integrate a 2×2 array of four identical tiles with a shared on-chip buffer, a simple interconnect, and a microprogrammed scheduler on a Xilinx Zynq UltraScale+ FPGA.

O3. Develop a basic mapping utility that converts a trained model (ONNX, restricted to a documented set of supported layers) into tile instructions and a schedule. Hand-tuning of the generated schedule is acceptable at this stage; a fully automatic optimising compiler is explicitly out of scope.

O4. Demonstrate two edge-relevant workloads on the same bitstream, switching between them in software only: (a) a compact image-classification CNN (MobileNet-class), and (b) a 1-D CNN for ECG arrhythmia classification.

O5. Publish a measured benchmark report: tile utilisation, latency, energy per inference versus the on-board ARM Cortex-A53 as baseline, and reconfiguration time.

4. Conceptualisation and Technical Approach

Architecture. Each RIA tile contains four elements: (i) an 8×8 INT8 MAC array for matrix and convolution arithmetic; (ii) a 16-lane vector unit implementing activations (ReLU family), pooling, and normalisation as short programs; (iii) dual-banked local SRAM so that the next layer's weights and instructions load while the current layer computes; and (iv) a sequencer that executes the loaded microprogram. A tile therefore behaves as a convolution engine in one layer and as an activation/pooling engine in the next, purely by instruction change.

System. Four tiles, a shared scratchpad buffer, DMA to external DDR memory, and a scheduler that dispatches per-layer work to tiles are integrated on the programmable logic of a Zynq UltraScale+ device. The on-chip ARM core acts as host and as the measurement baseline. The array size (2×2) is chosen to be large enough to demonstrate multi-tile scheduling and small enough to be completed and verified within 18 months by a small team.

Software (deliberately modest). The mapping utility parses an ONNX graph, checks it against the supported layer set (convolution, dense, ReLU-family activation, pooling, batch normalisation folding, quantisation to INT8), allocates layers to tiles, and emits instruction streams. It is a translation tool, not an optimising compiler; where automatic mapping is inefficient, schedules will be hand-adjusted and the adjustment documented. This honesty keeps the software effort proportionate to a proof-of-concept.

What is intentionally excluded: transformer/attention support, multi-FPGA scaling, automatic design-space exploration, and any ASIC work. These are follow-on activities, not commitments of this project.

5. Work Plan, Design and Delivery Milestones (18 months)

| Phase | Months | Work | Milestone (verifiable) |
| --- | --- | --- | --- |
| P1 | 1–3 | Tile micro-architecture specification; instruction set definition; testbench setup | M1: Frozen tile spec + ISA document |
| P2 | 4–7 | Single-tile RTL design and verification; synthesis on target FPGA | M2: One tile passing GEMM, convolution and vector test vectors on hardware |
| P3 | 8–11 | 2×2 array integration: shared buffer, DMA, scheduler; multi-tile test cases | M3: Four-tile array executing a multi-layer synthetic network |
| P4 | 10–14 | Mapping utility for the supported ONNX layer set; INT8 quantisation flow (overlaps P3) | M4: ECG model running end-to-end from ONNX input |
| P5 | 14–17 | Second workload (MobileNet-class CNN); performance and power measurement campaign | M5: Both models on one bitstream; measured benchmark tables |
| P6 | 17–18 | Benchmark report, documentation, publication and IP filing; TIC demonstration | M6: Public demo + final report to TIC |

Milestones M2, M3 and M5 are hardware demonstrations and can be witnessed by TIC reviewers on the bench.

6. Deliverables and Success Metrics

D1. Verified RTL of the RIA tile and 4-tile system (institution-owned IP).

D2. Working FPGA prototype demonstrating both workloads with software-only switching.

D3. Mapping utility and user documentation for the supported layer set.

D4. Measured benchmark report; at least one publication in a peer-reviewed VLSI/embedded-systems venue; one Indian patent application on the tile/scheduler mechanism.

D5. Four UG/PG students trained in accelerator design and two project associates skilled in RTL + ML deployment.

Quantitative success criteria:

| Metric | Target | How measured |
| --- | --- | --- |
| Average tile utilisation | ≥ 60% on both workloads | Hardware performance counters |
| Energy per inference | ≥ 5× better than ARM Cortex-A53 baseline on the same board | On-board power rails (PMBus) measurement |
| Model switch time | < 1 minute, software only (no re-synthesis) | Wall-clock, scripted |
| Reconfiguration overhead | < 5% of inference runtime | Cycle counters |
| Accuracy after INT8 quantisation | Within 1.5% of FP32 reference | Standard test sets (e.g., MIT-BIH for ECG) |

7. Prototype to Go-To-Market Strategy

This project delivers a laboratory-validated prototype (TRL 4–5). The commercialisation path beyond it is staged and realistic:

Near term (during project). The ECG demonstration is chosen deliberately: single-model, low-power medical and industrial monitoring devices are a market where FPGA-based deployment is already accepted, so the prototype itself is close to a usable reference design.

After the project (12–24 months). Package the design as an evaluation kit (board + mapping utility + documentation) for Indian device makers; incubate the activity through the institution's TBI with SASTRA–TCS TIC guidance; apply to the Design-Linked Incentive (DLI) scheme, for which a working FPGA prototype with measured results is the natural entry evidence.

Long term. Scale the tile array, extend the supported layer set, and license the design as semiconductor IP to Indian SoC companies. This is the ambition, but no deliverable of the present proposal depends on it.

8. Team Composition

<One-paragraph profile of the team lead / PI to be inserted here, per the call requirement: name, designation, relevant experience in VLSI/FPGA/embedded ML, key publications or projects.>

| Role | Count | Responsibility |
| --- | --- | --- |
| Principal Investigator (faculty) | 1 | Architecture, technical direction, reporting to TIC |
| Co-PI (faculty, VLSI/embedded) | 1 | Verification methodology, measurement campaign |
| Project Associates (full-time) | 2 | One RTL-focused, one software/ML-deployment-focused |
| UG/PG student members | 4 | Testbenches, model preparation, benchmarking, documentation |

9. Budget (Total: Rs. 50.00 Lakh)

Capital expenditure:

| # | Item | Amount (Rs. Lakh) |
| --- | --- | --- |
| 1 | 2 × AMD-Xilinx Zynq UltraScale+ FPGA development boards (ZCU104 class), incl. import duty/GST | 6.00 |
| 2 | 2 × development workstations (simulation and synthesis) | 4.00 |
| 3 | 1 × large-format 4K monitor (43") for waveform/layout debugging | 0.80 |
| 4 | Lab accessories: bench power supplies, JTAG programmers, current-measurement instrumentation, cabling, storage | 1.20 |
|  | Sub-total (capital) | 12.00 |

Software licences:

| # | Item | Amount (Rs. Lakh) |
| --- | --- | --- |
| 5 | 2 × AMD-Xilinx Vivado/Vitis design suite licences (18 months, node-locked seats — required for the target device) | 7.50 |
|  | Sub-total (software) | 7.50 |

Manpower (revenue):

| # | Item | Amount (Rs. Lakh) |
| --- | --- | --- |
| 6 | 2 × Project Associates @ Rs. 45,000/month × 18 months | 16.20 |
| 7 | UG/PG student stipends and internship support | 1.80 |
|  | Sub-total (manpower) | 18.00 |

Operations and other heads:

| # | Item | Amount (Rs. Lakh) |
| --- | --- | --- |
| 8 | Cloud compute for regression simulation and CI | 1.00 |
| 9 | Conference travel and registration (two national venues) | 1.50 |
| 10 | Publication charges and one Indian patent filing | 1.50 |
| 11 | Consumables (SD cards, adapters, spare components) | 0.50 |
| 12 | Contingency | 3.00 |
| 13 | Institutional overhead (10%) | 5.00 |
|  | Sub-total (operations & other) | 12.50 |

| Grand total | Rs. 50.00 Lakh |
| --- | --- |

10. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Tile RTL verification takes longer than planned | Array fixed at 2×2 and layer set frozen at M1; scope is cut (fewer supported layers), never extended, to protect milestones |
| Mapping utility proves harder than expected | Hand-written schedules are an accepted fallback for both demos; the utility then targets only the ECG model |
| Energy target (≥5× vs CPU) not met initially | Double-buffering and DMA batching are the known levers; the measurement campaign in P5 reserves time for two optimisation iterations |
| Staff attrition (project associates) | Overlapping student training from month 1 ensures continuity; documentation is a graded deliverable of every phase |

11. Institutional Facilities and TIC Alignment

The institution will provide laboratory space within campus (per the call requirement), existing computing infrastructure, and faculty time. Access to SASTRA facilities offered under the call will be used for measurement instrumentation and for the demonstration reviews at milestones M2, M3 and M5. The project matches the TIC objective of proof-of-concept to real-world impact: it ends with working hardware, measured numbers, a medical-adjacent demonstration, and a documented path into incubation — not with a report alone.